## Overview
gBlock Candidates — Status Overview
Where each of the 7 target genes stands, in plain terms. See the other tabs for details.
Gene target | Status | What this means | Species behind it | Next step
ureC | Ready to order | A finished candidate sequence, checked against the lab's primers and against a large, representative set of real bacteria. Two spots in the sequence are flagged for a quick expert double-check before ordering (see ureC tab). | 538 species | Have a team member confirm the two flagged spots, then send to synthesis.
nirS | Usable, but thin | A candidate sequence exists and passes the primer check, but it's built from only 2 real bacteria (a 3rd was too fragmented to use) because this gene is genuinely rare in this bacterial community. Treat as a working draft, not a fully confirmed community consensus. | 2 species | Decide whether 2 species is enough evidence to proceed, or whether to look for more reference data first.
nirK | Not ready — partial lead | One end of the target region (where the 'reverse' primer binds) checks out and looks trustworthy. The other end (the 'forward' primer) doesn't land on a consistent spot across the bacteria we checked, so a complete, reliable candidate sequence isn't ready yet. | 83 species checked; a reliable region found for one primer only | Needs a bioinformatics follow-up, and possibly a redesigned forward primer, before a candidate can be finalized.
amoA (AOB) | Not ready — too little data | Only 4 usable bacteria carry this gene in the entire reference community, which isn't enough to build a reliable community-representative sequence by any method. | 4 species | Likely needs additional reference bacteria beyond this dataset, or acceptance of a very limited sample.
nosZ clade I | Not ready | This gene is different enough between species that our standard alignment approach could only reliably line up a small handful of the bacteria that carry it, not enough to build a trustworthy community sequence yet. | 196 species carry the gene; only a handful could be reliably aligned | Needs a more advanced alignment approach or a narrower/different reference set.
nosZ clade II | Not ready | Same issue as nosZ clade I — this gene varies too much across species for our standard approach to confidently find the right target region. This gene also uses a special lab chemistry (inosine) at 2 primer spots that will need a substitution decision once a candidate exists. | 196 species carry the gene; not yet reliably aligned | Needs the same alignment follow-up as nosZ clade I, plus an inosine substitution decision later.
amoA (AOA) | Blocked — wrong reference data | This gene belongs to a different domain of life (Archaea) than every bacterium in our reference community, so there's nothing in our current data that could ever answer this one — it's not a matter of more analysis, it's missing the right starting data. | 0 (none in this dataset) | Needs a separate reference list of archaea before this can be worked on at all.

## ureC (ready to order)
ureC — Ready to Order
Built from 538 real bacteria, representative of the broader community this project studies.
Candidate sequence | TCCACACCTACCACACCGAAGGCGCCGGCGGCGGCCACGCGCCGGACATCATCAAGGTCGCCGGCCAGCCGAACGTGCTGCCGTCCTCGACCAACCCGACCCT
Length | 103 letters (bp)
Forward primer | TTCACACCTTCCACACCGAA
Reverse primer | AACGTCGGGTTGGTCGAG
Forward primer melting temp | 53.6°C
Reverse primer melting temp | 54.0°C
Primer check result | Passes — 2 mismatches on each end, within normal tolerance
Two spots to double-check before ordering | Positions 10 and 84 in the sequence changed when we corrected for a sampling imbalance earlier in the project. Both are real amino-acid-level changes (not just harmless spelling variants in the DNA), and haven't yet been checked against known important regions of this protein. Recommend a quick look by Gaurav/Brett or a literature check before finalizing.

## nirS (usable, thin)
nirS — Usable Candidate, Thin Evidence
Built from only 2 real bacteria (Halomonas nitroreducens and Halomonas cerina) — this gene is rare in the reference community, so this is the most complete picture currently possible, not a large-scale consensus like ureC.
Candidate sequence | AACGTCAAGGAAACCGGAAAGGTCCAGCTGGTCAACTACGAGGACCTGGACGCCCTGTCCACGGTGGAGATCGACACCTCCCGCTTCCTGCATGACGGCGGCTGGGACAGCACCGGCCGCTACTTCCTGACCGCGGCCAACGAGTCCAACCAGATCGTGGTCATCGACGCCCAGGAGCGCGAACTCGAGGCCATCGTCGACGTCGGCAAGATCCCCCACCCGGGACGCGGCGCCAACTTCGTCGACCCCGAGTTCGGGCCGGTCTGGGCCACCAGCCACCTCGGCGACAACACCATCCAGCTGATCGGCACCGACCCGGAAGGCCACCCCGACAACGCCTGGCAGGTGGTGCGCACCCTGCAAGGCCAGGGCGGCGGCTCGCTGTTCATCAAGACCCACCCCGAGTC
Length | 407 letters (bp)
Forward primer | AACGYSAAGGARACSGG
Reverse primer | GASTTCGGRTGSGTCTTSAYGAA (note: contains lab shorthand letters standing in for "either of two possible letters" at several spots — normal for this primer, not an error)
Forward primer melting temp (approximate) | 52.4°C
Reverse primer melting temp (approximate) | 56.6°C
Primer check result | Passes — 0 mismatches on the forward end, 2 on the reverse end, within normal tolerance
Caveat | Only 3 bacteria in the entire reference community carry this gene at all, and only 2 of those had usable sequence data. Recommend treating this as a working draft and discussing with the team whether more reference data should be sought before ordering.

## Not ready yet
Genes Not Yet Ready — Plain-Language Explanation
nirK
We found one reliable landmark (where the reverse primer binds) that's consistent across many of the bacteria that carry this gene — that part looks real and trustworthy. But the other landmark (the forward primer) doesn't line up consistently across those same bacteria, so we can't yet stitch together a complete, trustworthy candidate sequence. This looks like a genuine mismatch between the forward primer and this bacterial community, not a computer error on our end.
amoA (AOB)
Only 4 bacteria in the whole reference community carry this gene. That's too few to build a sequence that fairly represents "the community" by any method — any candidate built from 4 organisms would really just be describing those 4, not a broader picture.
nosZ clade I
This gene varies a lot in its DNA sequence from one type of bacteria to another, even though the underlying protein it makes is more similar than the DNA suggests. Our first-pass method for handling that (line up all the bacteria's sequences together, then find the matching region) only worked cleanly for a small handful of species. We tried a more sophisticated version of the same idea and it helped, but still not enough to trust the result yet.
nosZ clade II
Same underlying issue as nosZ clade I: too much natural variation across species for our current alignment method to confidently locate the primer target region for most of the bacteria involved. This gene also uses a special DNA building block (inosine) at 2 spots in its primers, which can't literally be manufactured into the final product — once a candidate sequence exists, we'll need to report what real DNA letter is most common at those two spots and use that instead. That step hasn't been reached yet because we don't have a reliable candidate sequence to check it against.
amoA (AOA)
This gene belongs to Archaea, a completely different branch of life from all the bacteria in our reference list. It's not that the analysis failed — there's simply nothing in our current data that could ever answer this question, the same way you couldn't identify a bird species using only a list of fish. We'd need an entirely separate reference list of archaea to make any progress here.

## How to read this
How to read this workbook
This project is designing 7 short reference DNA sequences ("gBlocks") — one per target gene — to use as positive controls in a lab test that measures nitrogen-cycle activity in poultry litter bacteria. Each gBlock needs to represent, as fairly as possible, what that gene actually looks like across the real mix of bacteria found in litter, not just one convenient reference organism. To do that, for each gene we: (1) checked which of ~1,584 real litter bacteria actually carry the gene, (2) pulled the real DNA sequence for that gene from each of those bacteria, (3) lined all those sequences up together and located the exact stretch the lab's primers target, and (4) built a single "typical" sequence from whatever real bacteria could be reliably compared. That process worked cleanly for ureC (538 bacteria) and, on a much smaller scale, for nirS (2 bacteria). For the other 5 genes, it ran into real limits — either too few bacteria carry the gene, the gene's sequence varies too much across species for our alignment method to confidently find the right stretch, or (for one gene) the reference bacteria list simply doesn't include the right kind of organism at all. None of those are computer errors — they're genuine findings about the reference data and the genes themselves, and they're explained in plain language on the "Not ready yet" tab. Bottom line: ureC is ready to send to synthesis (pending one quick expert check), nirS is usable but should be treated as a rough draft, and the remaining 5 genes need a follow-up decision from the team before a candidate sequence can be finalized.